## Sheet1
| M | T | W | T | F
5/2 -5/6 | N/A | AP Exam | Start writing the bare bone of the ClinetGUI class |  | Have the bare bones of the ClientGUI class finished just core functionality at this point nothing the looks the greatest
5/9 -5/13 | Have MessageHandeler class , Message class, and assocaiated unit test finished | Complete last touch ups to MessageHandeler based of the results of the testers | Start learning about multithreading so I can support multiple connections at the same time |  | Start writing the Server class with the knowledged how to support multiple clients
5/16 - 5/20 | Have the Server class finished, and start work on making the ClientGUI look nice | Start user testing with current version of instant messanger while continuing to work on the ClientGUI | Continue user testing | Have the ClientGUI class finished accounting for input from user testing | Work on createing my presentation and demo
5/23 - 5/27 | Be ready to present | Last minute touch ups to code, finishing off javadocs | · Presentations | Continue to polish demo and presentation if I have not gone yet | Presentations
· Code due 5pm
5/30-6/1 | Memorial Day |  | Presentations